## ค่าอุปกรณ์
การไฟฟ้าส่วนภูมิภาค รายละเอียดของงานเพื่อขออนุมัติเบิกจ่ายเงิน
งานก่อสร้างสถานีไฟฟ้า 115 เควี แบบ Terminal Substation พร้อมติดตั้งอุปกรณ์ 115 kV Air Break Switch จำนวน 1 ชุด ให้ บริษัท กัลฟ์ จะนะ กรีน จำกัด จังหวัดสงขลา
| สัญญาเลขที่/ใบสั่งจ้างเลขที่ TSD-22/2019 ลงวันที่ 09/09/2562 ผู้รับจ้าง บริษัท เด็มโก้ จำกัด (มหาชน) | [8 empty] | ค่าอุปกรณ์และค่าขนส่ง | งวดที่ | 2
id | ลำดับที่ | รายละเอียด |  | งานตามสัญญา |  |  |  |  | รวมงานที่ส่งมอบแล้ว |  | ส่งมอบงานครั้งนี้
|  |  |  | จำนวน | หน่วย | ราคาอุปกรณ์/หน่วย (บาท) | ค่าขนส่ง/หน่วย (บาท) | เป็นเงิน (บาท) | จำนวน | เป็นเงิน (บาท) | จำนวน | เป็นเงิน (บาท)
11777 |  | รายละเอียดค่าใช้จ่าย (PART A) อุปกรณ์สถานีไฟฟ้า
11778 | 1 | 115 kV Take off Structure & Bus Structure
11779 |  | 1.1 | Take off structure (Post) (Design by Contractor) | 4 | Set | 300000 | 10000 | 1240000 | 4 | 1240000
11780 |  | 1.2 | Take off structure (Beam) | 3 | Set | 200000 | 5000 | 615000 | 3 | 615000
11781 |  | 1.3 | Bus support structure | 9 | Set | 30000 | 1000 | 279000 | 9 | 279000
11782 |  | 1.4 | Area floodlight luminaires (250 W LED) with Terminal Box | 4 | Set | 30000 | 500 | 122000 | 4 | 122000
11783 | 2 | 115 kV Gas Circuit-Breaker
11784 |  | 2.1 | 115 kV circuit-breaker, SF6 gas, three - pole. 3150 A, 40 kA, 1 Sec., for 1YB-01 and 2YB-01 | 2 | Unit | By Owner |  |  | 2 | 20000
11785 |  | 2.2 | 115 kV circuit-breaker, SF6 gas, three - pole. 3150 A, 40 kA, 1 Sec. Creepage 31mm/kV for 3YB-01 | 1 | Unit | 1200000 | 10000 | 1210000 | 1 | 1210000
11786 |  | 2.3 | Supporting structure, for 2.1 | 2 | Set | By Owner |  |  | 2 | 2000
11787 |  | 2.4 | Supporting structure, for 2.2 | 1 | Set | 80000 | 1000 | 81000 | 1 | 81000
11788 |  | 2.5 | Operating platform for 2.1 | 2 | Set | By Owner |  |  | 2 | 1000
11789 |  | 2.6 | Operating platform for 2.2 | 1 | Set | 10000 | 500 | 10500 | 1 | 10500
11790 | 3 | 115 kV Disconnecting Switch, 2000A, 40 kA, 1 Sec.
11791 |  | 3.1 | 115 kV disconnecting switch, three-pole, with grounding switch for 1YS-02 and 2YS-02 | 2 | Unit | By Owner |  |  | 2 | 20000
11792 |  | 3.2 | 115 kV disconnecting switch, three-pole, with grounding switch 2000A,40 kA Creepage 31mm/kV for 3YS-02 | 4 | Unit | 540000 | 10000 | 2200000 | 4 | 2200000
11793 |  | 3.3 | Supporting structure, for 3.1 | 2 | Set | By Owner |  |  | 2 | 2000
11794 |  | 3.4 | Supporting structure, for 3.2 | 4 | Set | 70000 | 1000 | 284000 | 4 | 284000
11795 |  | 3.5 | Operating platform for 3.1 | 4 | Set | 10000 | 500 | 42000 | 4 | 42000
11796 |  | 3.6 | Operating platform for 3.2 | 8 | Set | 10000 | 500 | 84000 | 8 | 84000
11797 | 4 | 108kV Lightning arrester, 10 kA
11798 |  | 4.1 | 108 kV, 10 kA Lightning arrester, for 1YL-01 | 3 | Unit | By Owner |  |  |  |  | 0 | -
11799 |  | 4.2 | 108 kV, 10 kA Lightning arrester, for 2YL-01 and 3YL-01 | 6 | Unit | 80000 | 5000 | 510000 | 6 | 510000
11800 |  | 4.3 | Surge Counter, for 4.1 | 3 | Unit | By Owner |  |  |  |  | 0 | -
11801 |  | 4.4 | Surge Counter, for 4.2 | 6 | Unit | 15000 | 500 | 93000 | 6 | 93000
11802 |  | 4.5 | Supporting structure, for 4.1 | 3 | Set | By Owner |  |  |  |  | 0 | -
11803 |  | 4.6 | Supporting structure, for 4.2 | 6 | Set | 30000 | 1000 | 186000 | 6 | 186000
11804 | 5 | 115 kV Current transformer, 40 kA, 1 Sec.
11805 |  | 5.1 | 115 kV Current transformer, single-phase (for 1YC-01) | 3 | Unit | 350000 | 5000 | 1065000 | 3 | 1065000
11806 |  | 5.2 | 115 kV Current transformer, single-phase (for 2YC-01) | 3 | Unit | By Owner |  |  |  |  | 0 | -
11807 |  | 5.3 | 115 kV Current transformer, single-phase (for 3YC-01) | 3 | Unit | 350000 | 5000 | 1065000 | 3 | 1065000
11808 |  | 5.4 | Junction box, for 5.1 and 5.3 | 2 | Unit | 50000 | 1000 | 102000 | 2 | 102000
11809 |  | 5.5 | Junction box, for 5.2 | 1 | Unit | By Owner |  |  |  |  | 0 | -
11810 |  | 5.6 | Supporting structure, for 5.1 and 5.3 | 6 | Set | 30000 | 1000 | 186000 | 6 | 186000
11811 |  | 5.7 | Supporting structure, for 5.2 | 3 | Set | By Owner |  |  |  |  | 0 | -
11812 |  | 5.8 | Supporting structure, for 5.4 | 2 | Set | 5000 | 500 | 11000 | 2 | 11000
11813 |  | 5.9 | Supporting structure, for 5.5 | 1 | Set | By Owner |  |  | 1 | 500
11814 | 6 | 115 kV Voltage transformer
11815 |  | 6.1 | 115 kV Inductive voltage transformer, single-phase, for 1YP-01 | 3 | Unit | By Owner |  |  |  |  | 0 | -
11816 |  |  | - Ratio 115kV/ sqr.3 : 115/sqr.3 / 115V // 115/sqr.3 / 115 V // 115/sqr.3 / 115 V
11817 |  |  | - 200VA /CL0.2 , 200VA /3P, 200VA /3P,SIMULTANEOUS BURDEN=600VA
11818 |  | 6.2 | 115 kV Inductive voltage transformer, single-phase, for 2YP-01 | 3 | Unit | By Owner |  |  |  |  | 0 | -
11819 |  |  | - Ratio 115kV/ sqr.3 : 115/sqr.3 / 115V // 115/sqr.3 / 115 V // 115/sqr.3 / 115 V
11820 |  |  | - 200VA /CL0.2 , 200VA /3P, 200VA /3P,SIMULTANEOUS BURDEN=600VA
11821 |  | 6.3 | 115 kV Inductive voltage transformer, single-phase, for 3YP-01 | 3 | Unit | 350000 | 5000 | 1065000 | 3 | 1065000
11822 |  |  | - Ratio 115kV/ sqr.3 : 110/sqr.3 / 110V // 110/sqr.3 / 110 V // 110/sqr.3 / 110 V // 110/sqr.3 / 110 V
11823 |  |  | - 100VA /CL0.2 , 100VA /CL0.2 , 100VA /3P, 100VA /3P,SIMULTANEOUS BURDEN=400VA
11824 |  | 6.4 | Junction box, for 6.1 and 6.2 | 2 | Unit | By Owner |  |  |  |  | 0 | -
11825 |  | 6.5 | Junction box, for 6.3 | 1 | Unit | 50000 | 1000 | 51000 | 1 | 51000
11826 |  | 6.6 | Supporting structure, for 6.1 and 6.2 | 6 | Set | By Owner |  |  |  |  | 0 | -
11827 |  | 6.7 | Supporting structure, for 6.3 | 3 | Set | 30000 | 1000 | 93000 | 3 | 93000
11828 |  | 6.8 | Supporting structure, for 6.4 | 2 | Set | By Owner |  |  |  |  | 0 | -
11829 |  | 6.9 | Supporting structure, for 6.5 | 1 | Set | 5000 | 500 | 5500 | 1 | 5500
11830 |  | 6.1 | 115 kV Inductive voltage transformer, single-phase, for BYP-01 | 3 | Unit | By Owner |  |  |  |  | 0 | -
11831 |  |  | - Ratio 115kV/sqr.3 : 115/sqr.3 / 115V // 115/sqr.3 / 115 V // 115/sqr.3 / 115V
11832 |  |  | - 100VA /CL0.2 , 100VA /3P, 100VA /3P,SIMULTANEOUS BURDEN=300VA
11833 |  | 6.11 | Junction box, for 6.10 | 1 | Set | By Owner |  |  |  |  | 0 | -
11834 |  | 6.12 | Supporting structure, for 6.10 | 3 | Set | By Owner |  |  |  |  | 0 | -
11835 |  | 6.13 | Supporting structure, for 6.11 | 1 | Set | By Owner |  |  |  |  | 0 | -
11836 | 7 | Main Control Board
11837 |  | 7.1 | 115 kV Line Control & Protection Panel, for 1Y and 2Y | 2 | Unit | By Owner |  |  |  |  | 0 | -
11838 |  | 7.2 | 115 kV Line Control & Protection Panel, for 3Y | 1 | Unit | 2000000 | 5000 | 2005000 | 1 | 2005000
11839 |  | 7.3 | 115 kV Bus Differential panel (BZP) | 1 | Unit | By Owner |  |  |  |  | 0 | -
11840 |  |  | - Junction box for Bus Differential | 1 | Lot | 100000 | 2000 | 102000 | 1 | 102000
11841 |  |  | - Synchro Check panel | 1 | Lot | 200000 | 2000 | 202000 | 1 | 202000
11842 |  | 7.4 | Metering Panel | 1 | Lot | 300000 | 5000 | 305000 | 1 | 305000
11843 |  | 7.5 | Configuration, wiring & testing relay | 1 | Lot | 0 |  |  |  |  | 0 | 0
11844 | 8 | Teleprotection and Intertrip System
11845 |  | 8.1 | Teleprotection Equipment Board | 1 | Lot | By PEA |  |  |  |  | 0 | -
11846 |  | 8.2 | Relay configuration and testing, for teleprotection : 1Y, 2Y and 3Y | 1 | Lot | 0 |  |  |  |  | 0 | 0
11847 |  | 8.3 | 125Vdc Highspeed latching relay 3 sets & wiring, for Intertrip | 1 | Lot | 50000 | 1000 | 51000 |  |  | 0 | 0
11848 | 9 | EGAT Revenue Meter
11849 |  | 9.1 | EGAT Revunue meter panel | 1 | Unit | By Owner |  |  |  |  | 0 | -
11850 |  | 9.2 | External wiring & conduits | 1 | Lot | 0 |  |  |  |  | 0 | 0
11851 | 10 | 22/0.4 kV Station Service Transformer
11852 |  | 10.1 | Station service transformer, oil-immersed type,three-phase, 100 kVA, Dyn11, 33,000-400/230 VAC | 1 | Set | 250000 | 5000 | 255000 | 1 | 255000
11853 |  |  | installed on pole witn dropout fuse
11854 | 11 | AC and DC Distribution Board
11855 |  | 11.1 | AC Distribution Board ( 2 main CB, 30 branch circuits), Floor type | 1 | Set | 300000 | 5000 | 305000 | 1 | 305000
11856 |  | 11.2 | DC Distribution Board ( 2 main CB, 30 branch circuits), Floor type | 1 | Set | 300000 | 5000 | 305000 | 1 | 305000
11857 | 12 | Battery & Battery Charger For 125 VDC
11858 |  | 12.1 | Sealed Lead Acid Type Battery > 110 Ah 12V/block 125Vdc | 1 | Lot | 500000 | 5000 | 505000 | 1 | 505000
11859 |  | 12.2 | Steel Support for battery | 1 | Lot | 50000 | 1000 | 51000 | 1 | 51000
11860 |  | 12.3 | Battery Charger 30 A with automatic dropper switch | 2 | Set | 200000 | 5000 | 410000 | 2 | 410000
11861 |  | 12.4 | Safety switch with fuse | 1 | Set | 10000 | 500 | 10500 | 1 | 10500
11862 | 13 | Cable
11863 |  | 13.1 | L.V. power cable, NYY 750 V, for connecting between the AC distribution | 1 | Lot | 200000 | 3000 | 203000 | 1 | 203000
11864 |  |  | board and flood light, and ralated AC consumers
11865 |  | 13.2 | Control cable, 600 V, for connecting between the instrument transformers | 1 | Lot | 700000 | 5000 | 705000 | 1 | 705000
11866 |  |  | and the main control board
11867 |  | 13.3 | Control cable, 600 V, for connecting between the 115 kV. | 1 | Lot | 1500000 | 10000 | 1510000 | 1 | 1510000
11868 |  |  | Circuit Breakers (2.1), the 115 kV Disconnecting switches
11869 |  |  | (3.1 and 3.2) and the main control board (7.1 and 7.2) and between
11870 |  |  | the DC board and switchgear related DC consumers
11871 | 14 | Cable tray, Cable ladder and Conduit
11872 |  | 14.1 | Cable tray and Cable ladder with accessories | 1 | Lot | 200000 | 3000 | 203000 | 1 | 203000
11873 |  | 14.2 | Rigid steel conduits and fittings complete with accessories | 1 | Lot | 150000 | 3000 | 153000 | 1 | 153000
11874 |  | 14.3 | HDPE pipe (PN10) for floodlight, Dia 50 mm. complete with accessories | 1 | Lot | 100000 | 3000 | 103000 | 1 | 103000
11875 | 15 | Conductor, Substation Connector & Accessories
11876 |  | 15.1 | Pipe conductor, aluminium, size 1.500 in IPS | 1 | Lot | 80000 | 5000 | 85000 | 1 | 85000
11877 |  | 15.2 | Pipe conductor, aluminium, size 3.000 in IPS | 1 | Lot | 200000 | 5000 | 205000 | 1 | 205000
11878 |  | 15.3 | Pipe conductor fittings | 1 | Lot | 50000 | 2000 | 52000 | 1 | 52000
11879 |  | 15.4 | Stranded conductor, aluminium, 240 sq.mm | 1 | Lot | 70000 | 500 | 70500 | 1 | 70500
11880 |  | 15.5 | Stranded conductor, aluminium, 400 sq.mm | 1 | Lot | 100000 | 500 | 100500 | 1 | 100500
11881 |  | 15.6 | Stranded conductor accessories | 1 | Lot | 50000 | 500 | 50500 | 1 | 50500
11882 |  | 15.7 | Substation connectors | 1 | Lot | 500000 | 3000 | 503000 | 1 | 503000
11883 |  | 15.8 | Wire, Steel Stranded, 50/7 sq.mm. | 1 | Lot | 80000 | 500 | 80500 | 1 | 80500
11884 |  | 15.9 | Shield wire steel stranded accessories | 1 | Lot | 50000 | 500 | 50500 | 1 | 50500
11885 | 16 | Insulator
11886 |  | 16.1 | Insulator, suspension type, Class 52-3, for 115 kV. string assemblies | 1 | Lot | 80000 | 1000 | 81000 | 1 | 81000
11887 |  | 16.2 | Insulator, suspension type, Class 52-8, for 115 kV. string assemblies | 1 | Lot | 100000 | 1000 | 101000 | 1 | 101000
11888 |  | 16.3 | Insulator, station post type, ANSI Technical Reference No. 286, for 115 kV. | 1 | Lot | 500000 | 3000 | 503000 | 1 | 503000
11889 |  |  | bus support structure
11890 | 17 | Earthing System Equipment
11891 |  | 17.1 | Earthing system in switchyard & Control Building (Excluding conductor 95 Sq.mm.) | 1 | Lot | 500000 | 3000 | 503000 | 1 | 503000
11892 |  | 17.2 | Conductor , Copper , Bare 95 sq.mm. | 1 | Lot | 700000 | 3000 | 703000 | 1 | 703000
11893 |  | 17.3 | Ground rod, Copper covered steel, diameter 16 mm. or 5/8" 3,000 mm. long | 1 | Lot | 300000 | 3000 | 303000 | 1 | 303000
11894 |  | 17.4 | Earthing system in control building | 1 | Lot | 100000 | 1000 | 101000 | 1 | 101000
11895 | 18 | Identification plate and danger notice
11896 |  | 18.1 | Identification plates and danger notice | 1 | Lot | 50000 | 500 | 50500 | 1 | 50500
11897 |  | 18.2 | Other nescessary materials | 1 | Lot | 20000 | 500 | 20500 | 1 | 20500
11898 | 19 | Fire Barrier System
11899 |  | 19.1 | Fire barrier for control building | 1 | Lot | 50000 | 1000 | 51000 |  |  | 0 | 0
11900 | 20 | 115 kV Air Break Switch
11901 |  | 20.1 | 115kV Air break switch 2000A 100kA with steel support | 1 | Set | 900000 | 8000 | 908000 | 1 | 908000
11902 |  | 20.2 | 115kV Transmission Line | 1 | Lot | 500000 | 10000 | 510000 | 1 | 510000
11903 | 21 | 33kV Internal Distribuiton System
11904 |  | 21.1 | 33kV Overhead distribuilding system connect between PEA system to station service transformer | 1 | Lot | 1000000 | 5000 | 1005000 | 1 | 1005000
11905 | 22 | Test, Commissioning & As-Built Drawing
11906 |  | 22.1 | Factory Acceptance Test (Accuracy Test) for 5.1 & 5.3 , 6.3 [6 Persons] | 1 | Lot | 0 |  |  | 1 | 0
11907 |  | 22.2 | Individual Test & Commissioning Test | 1 | Lot | None |  |  |  |  | 0 | -
11908 |  | 22.3 | As-Built Drawing & Instruction Manual | 1 | Lot | 100000 |  |  |  |  | 0 | 0
11909 |  | รายละเอียดค่าใช้จ่าย (PART B) งานโยธาสถานีไฟฟ้า
11910 | 1 | Sub-soil test from ground surface to not less than 30.00 m. depth. |  | 2 | Bores | 35000 |  |  | 2 | 70000
11911 | 2 | Control building
11912 |  | - | Control building 6 x 6 x (1.5+3.5) m on pile (w x l x h) | 1 | Lot | 3000000 |  |  | 0.9 | 2700000 | 0 | 0
11913 |  | - | Epoxy floor (green/red colur), self leveling | 1 | Lot | 200000 |  |  | 0.9 | 180000 | 0 | 0
11914 | 3 | Faciltity for control building
11915 |  | - | 2x36 watt lighting fixture with reflector | 8 | Set | 2000 |  |  | 8 | 16000
11916 |  | - | 2x36 watt lighting fixture with reflector (Acid proof) | 1 | Set | 5000 |  |  | 1 | 5000
11917 |  | - | 1x36 watt lighting fixture (Weather proof) | 4 | Set | 2500 |  |  | 4 | 10000
11918 |  | - | Receptacle | 4 | Set | 1500 |  |  | 4 | 6000
11919 |  | - | Air condition 36,000 Btu | 2 | Set | 55000 |  |  | 2 | 110000
11920 |  | - | Air condition control panel | 1 | Set | 3000 |  |  | 1 | 3000
11921 |  | - | Ventilation (Fan) | 2 | Set | 3000 |  |  | 2 | 6000
11922 |  | - | Emergency lighting 2x50 w | 2 | Set | 4000 |  |  | 2 | 8000
11923 |  | - | Switch, wire, conductor, conduit and accessories | 1 | Lot | 10000 |  |  | 1 | 10000
11924 |  | - | Fire extinguisher (CO2) | 2 | Set | 5000 |  |  | 2 | 10000
11925 | 4 | Fire alarm system
11926 |  | - | Hardwire system 2 Zone (Manual ,Detector) | 1 | Set | 50000 |  |  | 1 | 50000
11927 |  | - | Heat detector (battery room) | 1 | Set | 4000 |  |  | 1 | 4000
11928 |  | - | Smoke detector (control room) | 2 | Set | 2000 |  |  | 2 | 4000
11929 |  | - | Bell alarm | 1 | Set | 4000 |  |  | 1 | 4000
11930 |  | - | wire conductor (Fire resistance) ,conduit and accessories | 1 | Lot | 50000 |  |  | 1 | 50000
11931 | 5 | Switchyard and Foundation, On pile
11932 |  | - | 115 kV Take-off structure foundation | 4 | Set | 230000 |  |  | 4 | 920000
11933 |  | - | 115 kV Disconnecting Switch foundation | 6 | Set | 120000 |  |  | 6 | 720000
11934 |  | - | 108 kV 10kA Lightning arrester foundation | 9 | Set | 50000 |  |  | 9 | 450000
11935 |  | - | 115 kV Bus support foundation | 9 | Set | 30000 |  |  | 9 | 270000
11936 |  | - | 115 kV Current transformer foundation | 9 | Set | 50000 |  |  | 9 | 450000
11937 |  | - | 115 kV Voltage transformer foundation | 12 | Set | 50000 |  |  | 12 | 600000
11938 |  | - | 115 kV Circuit-breaker foundation | 3 | Set | 120000 |  |  | 3 | 360000
11939 | 6 | Retening wall 3.00 m depth |  | 30 | m | 35000 |  |  | 30 | 1050000
11940 | 7 | Lamp post foundation., On 4 x Hex x pile dia 0.15 x 6m. |  | 8 | Set | 30000 |  |  | 8 | 240000
11941 | 8 | Cable trench with steel cover, size 0.80 m and 1.20 m |  | 1 | Lot | 600000 |  |  | 0.9 | 540000 | 0.1 | 60000
11942 | 9 | HDPE Dia 63 mm. PN8 and accessories (for lamp post circuit) |  | 1 | Lot | 300000 |  |  | 1 | 300000
11943 | 10 | Crushed rock No.2 surfacing, 10 cm. height with concrete curb |  | 1 | Lot | 450000 |  |  | 0.8 | 360000 | 0 | 0
11944 | 11 | RC Trench with RC cover or PVC pipe in substation (for rain drainge system) |  | 1 | Lot | 550000 |  |  | 0.5 | 275000 | 0 | 0
11945 | 12 | RC pipe or PVC. pipe and RC manhole (for control building) |  | 1 | Lot | 500000 |  |  | 0.8 | 400000 | 0 | 0
11946 | 13 | Wire mesh fence |  | 1 | Lot | 500000 |  |  |  |  | 0 | 0
11947 | 14 | Mesh gate (rolling door) 6 m width |  | 1 | Lot | 150000 |  |  |  |  | 0 | 0
11948 | 15 | Concrete road 6 m width connect between existing road to substation |  | 1 | Lot | 380000 |  |  | 1 | 380000
11949 | 16 | Civil Engineering design and Permissive Fee (Architecture ,civil) |  | 1 | Lot | 300000 |  |  | 0.9 | 270000 | 0 | 0
11950 | 17 | Temporary fence and toilet |  | 1 | Lot | 250000 |  |  | 0.9 | 225000 | 0 | 0
11951 | 18 | Toilet with sanitary ware |  | 1 | Lot | 330000 |  |  |  |  | 0 | 0
11952 | 19 | งานคืนสภาพพื้นที่ก่อสร้าง |  | 1 | Lot | 400000 |  |  |  |  | 0 | 0
11953 |  | รายละเอียดค่าใช้จ่าย (PART C) อุปกรณ์สำนักงานสำหรับใช้หน้างาน
11954 | 1 | อุปกรณ์ประกอบการใช้งานสนาม
11955 |  | - | เช่าตู้ Mobile Office และโต๊ะ เก้าอี้ทำงาน | 1 | Lot | 150000 | 10000 | 160000 | 1 | 160000
11956 |  | - | เช่ารถยนต์ส่วนบุคคล (รถเก๋ง) เกียร์ออโต้ 4 ประตู 4 ที่นั่ง 1,600 ซีซี (อายุไม่เกิน 3 ปี) | 1 | Lot | 324000 |  |  |  |  | 0 | 0
11957 |  |  | พร้อม พรบ. ประกันชั้น 1 และภาษีประจำปี จำนวน 3 คัน จำนวน 6 เดือน
11958 |  |  | และต้องเป็นรถยนต์จากบริษัทที่ดำเนินธุรกิจรถยนต์เช่า

## ค่าติดตั้งทดสอบ
การไฟฟ้าส่วนภูมิภาค รายละเอียดของงานเพื่อขออนุมัติเบิกจ่ายเงิน
งานก่อสร้างสถานีไฟฟ้า 115 เควี แบบ Terminal Substation พร้อมติดตั้งอุปกรณ์ 115 kV Air Break Switch จำนวน 1 ชุด ให้ บริษัท กัลฟ์ จะนะ กรีน จำกัด จังหวัดสงขลา
| สัญญาเลขที่/ใบสั่งจ้างเลขที่ TSD-22/2019 ลงวันที่ 09/09/2562 ผู้รับจ้าง บริษัท เด็มโก้ จำกัด (มหาชน) | [7 empty] | ค่าติดตั้งและทดสอบ | งวดที่ | 2
id | ลำดับที่ | รายละเอียด |  | งานตามสัญญา |  |  |  | รวมงานที่ส่งมอบแล้ว |  | ส่งมอบงานครั้งนี้
|  |  |  | จำนวน | หน่วย | ราคาติดตั้งทดสอบ/หน่วย (บาท) | เป็นเงิน (บาท) | จำนวน | เป็นเงิน (บาท) | จำนวน | เป็นเงิน (บาท)
11777 |  | รายละเอียดค่าใช้จ่าย (PART A) อุปกรณ์สถานีไฟฟ้า
11778 | 1 | 115 kV Take off Structure & Bus Structure
11779 |  | 1.1 | Take off structure (Post) (Design by Contractor) | 4 | Set | 10000 | 40000 | 4 | 40000 | 0
11780 |  | 1.2 | Take off structure (Beam) | 3 | Set | 5000 | 15000 | 3 | 15000 | 0
11781 |  | 1.3 | Bus support structure | 9 | Set | 3000 | 27000 | 9 | 27000 | 0
11782 |  | 1.4 | Area floodlight luminaires (250 W LED) with Terminal Box | 4 | Set | 2000 | 8000 | 0 |  | 0 | 0
11783 | 2 | 115 kV Gas Circuit-Breaker
11784 |  | 2.1 | 115 kV circuit-breaker, SF6 gas, three - pole. 3150 A, 40 kA, 1 Sec., for 1YB-01 and 2YB-01 | 2 | Unit | 100000 | 200000 | 0 |  | 0 | 0
11785 |  | 2.2 | 115 kV circuit-breaker, SF6 gas, three - pole. 3150 A, 40 kA, 1 Sec. Creepage 31mm/kV for 3YB-01 | 1 | Unit | 100000 | 100000 | 0 |  | 0 | 0
11786 |  | 2.3 | Supporting structure, for 2.1 | 2 | Set | 5000 | 10000 | 0 |  | 0 | 0
11787 |  | 2.4 | Supporting structure, for 2.2 | 1 | Set | 5000 | 5000 | 0 |  | 0 | 0
11788 |  | 2.5 | Operating platform for 2.1 | 2 | Set | 1000 | 2000 | 0 |  | 0 | 0
11789 |  | 2.6 | Operating platform for 2.2 | 1 | Set | 1000 | 1000 | 0 |  | 0 | 0
11790 | 3 | 115 kV Disconnecting Switch, 2000A, 40 kA, 1 Sec.
11791 |  | 3.1 | 115 kV disconnecting switch, three-pole, with grounding switch for 1YS-02 and 2YS-02 | 2 | Unit | 100000 | 200000 | 0 |  | 0 | 0
11792 |  | 3.2 | 115 kV disconnecting switch, three-pole, with grounding switch 2000A,40 kA Creepage 31mm/kV for 3YS-02 | 4 | Unit | 100000 | 400000 | 0 |  | 0 | 0
11793 |  | 3.3 | Supporting structure, for 3.1 | 2 | Set | 5000 | 10000 | 0 |  | 0 | 0
11794 |  | 3.4 | Supporting structure, for 3.2 | 4 | Set | 5000 | 20000 | 0 |  | 0 | 0
11795 |  | 3.5 | Operating platform for 3.1 | 4 | Set | 1000 | 4000 | 0 |  | 0 | 0
11796 |  | 3.6 | Operating platform for 3.2 | 8 | Set | 1000 | 8000 | 0 |  | 0 | 0
11797 | 4 | 108kV Lightning arrester, 10 kA
11798 |  | 4.1 | 108 kV, 10 kA Lightning arrester, for 1YL-01 | 3 | Unit | 30000 | 90000 | 0 |  | 0 | 0
11799 |  | 4.2 | 108 kV, 10 kA Lightning arrester, for 2YL-01 and 3YL-01 | 6 | Unit | 30000 | 180000 | 0 |  | 0 | 0
11800 |  | 4.3 | Surge Counter, for 4.1 | 3 | Unit | 3000 | 9000 | 0 |  | 0 | 0
11801 |  | 4.4 | Surge Counter, for 4.2 | 6 | Unit | 3000 | 18000 | 0 |  | 0 | 0
11802 |  | 4.5 | Supporting structure, for 4.1 | 3 | Set | 1000 | 3000 | 0 |  | 0 | 0
11803 |  | 4.6 | Supporting structure, for 4.2 | 6 | Set | 1000 | 6000 | 0 |  | 0 | 0
11804 | 5 | 115 kV Current transformer, 40 kA, 1 Sec.
11805 |  | 5.1 | 115 kV Current transformer, single-phase (for 1YC-01) | 3 | Unit | 50000 | 150000 | 0 |  | 0 | 0
11806 |  | 5.2 | 115 kV Current transformer, single-phase (for 2YC-01) | 3 | Unit | 50000 | 150000 | 0 |  | 0 | 0
11807 |  | 5.3 | 115 kV Current transformer, single-phase (for 3YC-01) | 3 | Unit | 50000 | 150000 | 0 |  | 0 | 0
11808 |  | 5.4 | Junction box, for 5.1 and 5.3 | 2 | Unit | 2000 | 4000 | 0 |  | 0 | 0
11809 |  | 5.5 | Junction box, for 5.2 | 1 | Unit | 2000 | 2000 | 0 |  | 0 | 0
11810 |  | 5.6 | Supporting structure, for 5.1 and 5.3 | 6 | Set | 3000 | 18000 | 0 |  | 0 | 0
11811 |  | 5.7 | Supporting structure, for 5.2 | 3 | Set | 3000 | 9000 | 0 |  | 0 | 0
11812 |  | 5.8 | Supporting structure, for 5.4 | 2 | Set | 1000 | 2000 | 0 |  | 0 | 0
11813 |  | 5.9 | Supporting structure, for 5.5 | 1 | Set | 1000 | 1000 | 0 |  | 0 | 0
11814 | 6 | 115 kV Voltage transformer
11815 |  | 6.1 | 115 kV Inductive voltage transformer, single-phase, for 1YP-01 | 3 | Unit | 50000 | 150000 | 0 |  | 0 | 0
11816 |  |  | - Ratio 115kV/ sqr.3 : 115/sqr.3 / 115V // 115/sqr.3 / 115 V // 115/sqr.3 / 115 V
11817 |  |  | - 200VA /CL0.2 , 200VA /3P, 200VA /3P,SIMULTANEOUS BURDEN=600VA
11818 |  | 6.2 | 115 kV Inductive voltage transformer, single-phase, for 2YP-01 | 3 | Unit | 50000 | 150000 | 0 |  | 0 | 0
11819 |  |  | - Ratio 115kV/ sqr.3 : 115/sqr.3 / 115V // 115/sqr.3 / 115 V // 115/sqr.3 / 115 V
11820 |  |  | - 200VA /CL0.2 , 200VA /3P, 200VA /3P,SIMULTANEOUS BURDEN=600VA
11821 |  | 6.3 | 115 kV Inductive voltage transformer, single-phase, for 3YP-01 | 3 | Unit | 50000 | 150000 | 0 |  | 0 | 0
11822 |  |  | - Ratio 115kV/ sqr.3 : 110/sqr.3 / 110V // 110/sqr.3 / 110 V // 110/sqr.3 / 110 V // 110/sqr.3 / 110 V
11823 |  |  | - 100VA /CL0.2 , 100VA /CL0.2 , 100VA /3P, 100VA /3P,SIMULTANEOUS BURDEN=400VA
11824 |  | 6.4 | Junction box, for 6.1 and 6.2 | 2 | Unit | 2000 | 4000 | 0 |  | 0 | 0
11825 |  | 6.5 | Junction box, for 6.3 | 1 | Unit | 2000 | 2000 | 0 |  | 0 | 0
11826 |  | 6.6 | Supporting structure, for 6.1 and 6.2 | 6 | Set | 3000 | 18000 | 0 |  | 0 | 0
11827 |  | 6.7 | Supporting structure, for 6.3 | 3 | Set | 3000 | 9000 | 0 |  | 0 | 0
11828 |  | 6.8 | Supporting structure, for 6.4 | 2 | Set | 1000 | 2000 | 0 |  | 0 | 0
11829 |  | 6.9 | Supporting structure, for 6.5 | 1 | Set | 1000 | 1000 | 0 |  | 0 | 0
11830 |  | 6.1 | 115 kV Inductive voltage transformer, single-phase, for BYP-01 | 3 | Unit | 50000 | 150000 | 0 |  | 0 | 0
11831 |  |  | - Ratio 115kV/sqr.3 : 115/sqr.3 / 115V // 115/sqr.3 / 115 V // 115/sqr.3 / 115V
11832 |  |  | - 100VA /CL0.2 , 100VA /3P, 100VA /3P,SIMULTANEOUS BURDEN=300VA
11833 |  | 6.11 | Junction box, for 6.10 | 1 | Set | 2000 | 2000 | 0 |  | 0 | 0
11834 |  | 6.12 | Supporting structure, for 6.10 | 3 | Set | 3000 | 9000 | 0 |  | 0 | 0
11835 |  | 6.13 | Supporting structure, for 6.11 | 1 | Set | 1000 | 1000 | 0 |  | 0 | 0
11836 | 7 | Main Control Board
11837 |  | 7.1 | 115 kV Line Control & Protection Panel, for 1Y and 2Y | 2 | Unit | 80000 | 160000 | 0 |  | 0 | 0
11838 |  | 7.2 | 115 kV Line Control & Protection Panel, for 3Y | 1 | Unit | 80000 | 80000 | 0 |  | 0 | 0
11839 |  | 7.3 | 115 kV Bus Differential panel (BZP) | 1 | Unit | 80000 | 80000 | 0 |  | 0 | 0
11840 |  |  | - Junction box for Bus Differential | 1 | Lot | 5000 | 5000 | 0 |  | 0 | 0
11841 |  |  | - Synchro Check panel | 1 | Lot | 5000 | 5000 | 0 |  | 0 | 0
11842 |  | 7.4 | Metering Panel | 1 | Lot | 5000 | 5000 | 0 |  | 0 | 0
11843 |  | 7.5 | Configuration, wiring & testing relay | 1 | Lot | 20000 | 20000 | 0 |  | 0 | 0
11844 | 8 | Teleprotection and Intertrip System
11845 |  | 8.1 | Teleprotection Equipment Board | 1 | Lot | By PEA |  | 0 |  | 0 | -
11846 |  | 8.2 | Relay configuration and testing, for teleprotection : 1Y, 2Y and 3Y | 1 | Lot | 3000 | 3000 | 0 |  | 0 | 0
11847 |  | 8.3 | 125Vdc Highspeed latching relay 3 sets & wiring, for Intertrip | 1 | Lot | 2000 | 2000 | 0 |  | 0 | 0
11848 | 9 | EGAT Revenue Meter
11849 |  | 9.1 | EGAT Revunue meter panel | 1 | Unit | 15000 | 15000 | 0 |  | 0 | 0
11850 |  | 9.2 | External wiring & conduits | 1 | Lot | 20000 | 20000 | 0 |  | 0 | 0
11851 | 10 | 22/0.4 kV Station Service Transformer
11852 |  | 10.1 | Station service transformer, oil-immersed type,three-phase, 100 kVA, Dyn11, 33,000-400/230 VAC | 1 | Set | 20000 | 20000 | 0 |  | 0 | 0
11853 |  |  | installed on pole witn dropout fuse
11854 | 11 | AC and DC Distribution Board
11855 |  | 11.1 | AC Distribution Board ( 2 main CB, 30 branch circuits), Floor type | 1 | Set | 5000 | 5000 | 0 |  | 0 | 0
11856 |  | 11.2 | DC Distribution Board ( 2 main CB, 30 branch circuits), Floor type | 1 | Set | 5000 | 5000 | 0 |  | 0 | 0
11857 | 12 | Battery & Battery Charger For 125 VDC
11858 |  | 12.1 | Sealed Lead Acid Type Battery > 110 Ah 12V/block 125Vdc | 1 | Lot | 30000 | 30000 | 0 |  | 0 | 0
11859 |  | 12.2 | Steel Support for battery | 1 | Lot | 1000 | 1000 | 0 |  | 0 | 0
11860 |  | 12.3 | Battery Charger 30 A with automatic dropper switch | 2 | Set | 5000 | 10000 | 0 |  | 0 | 0
11861 |  | 12.4 | Safety switch with fuse | 1 | Set | 1000 | 1000 | 0 |  | 0 | 0
11862 | 13 | Cable
11863 |  | 13.1 | L.V. power cable, NYY 750 V, for connecting between the AC distribution | 1 | Lot | 10000 | 10000 | 0 |  | 0 | 0
11864 |  |  | board and flood light, and ralated AC consumers
11865 |  | 13.2 | Control cable, 600 V, for connecting between the instrument transformers | 1 | Lot | 45000 | 45000 | 0 |  | 0 | 0
11866 |  |  | and the main control board
11867 |  | 13.3 | Control cable, 600 V, for connecting between the 115 kV. | 1 | Lot | 100000 | 100000 | 0 |  | 0 | 0
11868 |  |  | Circuit Breakers (2.1), the 115 kV Disconnecting switches
11869 |  |  | (3.1 and 3.2) and the main control board (7.1 and 7.2) and between
11870 |  |  | the DC board and switchgear related DC consumers
11871 | 14 | Cable tray, Cable ladder and Conduit
11872 |  | 14.1 | Cable tray and Cable ladder with accessories | 1 | Lot | 2000 | 2000 | 1 | 2000 | 0
11873 |  | 14.2 | Rigid steel conduits and fittings complete with accessories | 1 | Lot | 2000 | 2000 | 0 |  | 0 | 0
11874 |  | 14.3 | HDPE pipe (PN10) for floodlight, Dia 50 mm. complete with accessories | 1 | Lot | 2000 | 2000 | 0 |  | 0 | 0
11875 | 15 | Conductor, Substation Connector & Accessories
11876 |  | 15.1 | Pipe conductor, aluminium, size 1.500 in IPS | 1 | Lot | 10000 | 10000 | 0 |  | 0 | 0
11877 |  | 15.2 | Pipe conductor, aluminium, size 3.000 in IPS | 1 | Lot | 30000 | 30000 | 0 |  | 0 | 0
11878 |  | 15.3 | Pipe conductor fittings | 1 | Lot | 2000 | 2000 | 0 |  | 0 | 0
11879 |  | 15.4 | Stranded conductor, aluminium, 240 sq.mm | 1 | Lot | 3000 | 3000 | 0 |  | 0 | 0
11880 |  | 15.5 | Stranded conductor, aluminium, 400 sq.mm | 1 | Lot | 3000 | 3000 | 0 |  | 0 | 0
11881 |  | 15.6 | Stranded conductor accessories | 1 | Lot | 1000 | 1000 | 0 |  | 0 | 0
11882 |  | 15.7 | Substation connectors | 1 | Lot | 50000 | 50000 | 0 |  | 0 | 0
11883 |  | 15.8 | Wire, Steel Stranded, 50/7 sq.mm. | 1 | Lot | 1000 | 1000 | 0 |  | 0 | 0
11884 |  | 15.9 | Shield wire steel stranded accessories | 1 | Lot | 1000 | 1000 | 0 |  | 0 | 0
11885 | 16 | Insulator
11886 |  | 16.1 | Insulator, suspension type, Class 52-3, for 115 kV. string assemblies | 1 | Lot | 3000 | 3000 | 0 |  | 0 | 0
11887 |  | 16.2 | Insulator, suspension type, Class 52-8, for 115 kV. string assemblies | 1 | Lot | 3000 | 3000 | 0 |  | 0 | 0
11888 |  | 16.3 | Insulator, station post type, ANSI Technical Reference No. 286, for 115 kV. | 1 | Lot | 20000 | 20000 | 0 |  | 0 | 0
11889 |  |  | bus support structure
11890 | 17 | Earthing System Equipment
11891 |  | 17.1 | Earthing system in switchyard & Control Building (Excluding conductor 95 Sq.mm.) | 1 | Lot | 10000 | 10000 | 1 | 10000 | 0
11892 |  | 17.2 | Conductor , Copper , Bare 95 sq.mm. | 1 | Lot | 20000 | 20000 | 1 | 20000 | 0
11893 |  | 17.3 | Ground rod, Copper covered steel, diameter 16 mm. or 5/8" 3,000 mm. long | 1 | Lot | 10000 | 10000 | 0 |  | 0 | 0
11894 |  | 17.4 | Earthing system in control building | 1 | Lot | 10000 | 10000 | 1 | 10000 | 0
11895 | 18 | Identification plate and danger notice
11896 |  | 18.1 | Identification plates and danger notice | 1 | Lot | 5000 | 5000 | 0 |  | 0 | 0
11897 |  | 18.2 | Other nescessary materials | 1 | Lot | 1000 | 1000 | 0 |  | 0 | 0
11898 | 19 | Fire Barrier System
11899 |  | 19.1 | Fire barrier for control building | 1 | Lot | 5000 | 5000 | 0 |  | 0 | 0
11900 | 20 | 115 kV Air Break Switch
11901 |  | 20.1 | 115kV Air break switch 2000A 100kA with steel support | 1 | Set | 30000 | 30000 | 0 |  | 0 | 0
11902 |  | 20.2 | 115kV Transmission Line | 1 | Lot | 20000 | 20000 | 0 |  | 0 | 0
11903 | 21 | 33kV Internal Distribuiton System
11904 |  | 21.1 | 33kV Overhead distribuilding system connect between PEA system to station service transformer | 1 | Lot | 50000 | 50000 | 1 | 50000 | 0
11905 | 22 | Test, Commissioning & As-Built Drawing
11906 |  | 22.1 | Factory Acceptance Test (Accuracy Test) for 5.1 & 5.3 , 6.3 [6 Persons] | 1 | Lot | 900000 | 900000 | 1 | 900000 | 0
11907 |  | 22.2 | Individual Test & Commissioning Test | 1 | Lot | None |  | 0 |  | 0 | -
11908 |  | 22.3 | As-Built Drawing & Instruction Manual | 1 | Lot | 0 | 0 | 0 |  | 0 | 0
11909 |  | รายละเอียดค่าใช้จ่าย (PART B) งานโยธาสถานีไฟฟ้า
11910 | 1 | Sub-soil test from ground surface to not less than 30.00 m. depth. |  | 2 | Bores | 20000 | 40000 | 2 | 40000 | 0
11911 | 2 | Control building
11912 |  | - | Control building 6 x 6 x (1.5+3.5) m on pile (w x l x h) | 1 | Lot | 200000 | 200000 | 0.9 | 180000 | 0 | 0
11913 |  | - | Epoxy floor (green/red colur), self leveling | 1 | Lot | 50000 | 50000 | 0.9 | 45000 | 0 | 0
11914 | 3 | Faciltity for control building
11915 |  | - | 2x36 watt lighting fixture with reflector | 8 | Set | 500 | 4000 | 8 | 4000 | 0
11916 |  | - | 2x36 watt lighting fixture with reflector (Acid proof) | 1 | Set | 500 | 500 | 1 | 500 | 0
11917 |  | - | 1x36 watt lighting fixture (Weather proof) | 4 | Set | 500 | 2000 | 4 | 2000 | 0
11918 |  | - | Receptacle | 4 | Set | 200 | 800 | 4 | 800 | 0
11919 |  | - | Air condition 36,000 Btu | 2 | Set | 10000 | 20000 | 2 | 20000 | 0
11920 |  | - | Air condition control panel | 1 | Set | 2000 | 2000 | 1 | 2000 | 0
11921 |  | - | Ventilation (Fan) | 2 | Set | 1000 | 2000 | 2 | 2000 | 0
11922 |  | - | Emergency lighting 2x50 w | 2 | Set | 500 | 1000 | 2 | 1000 | 0
11923 |  | - | Switch, wire, conductor, conduit and accessories | 1 | Lot | 2000 | 2000 | 1 | 2000 | 0
11924 |  | - | Fire extinguisher (CO2) | 2 | Set | 1000 | 2000 | 0 |  | 0 | 0
11925 | 4 | Fire alarm system
11926 |  | - | Hardwire system 2 Zone (Manual ,Detector) | 1 | Set | 5000 | 5000 | 0 |  | 0 | 0
11927 |  | - | Heat detector (battery room) | 1 | Set | 500 | 500 | 0 |  | 0 | 0
11928 |  | - | Smoke detector (control room) | 2 | Set | 350 | 700 | 0 |  | 0 | 0
11929 |  | - | Bell alarm | 1 | Set | 500 | 500 | 0 |  | 0 | 0
11930 |  | - | wire conductor (Fire resistance) ,conduit and accessories | 1 | Lot | 1000 | 1000 | 0 |  | 0 | 0
11931 | 5 | Switchyard and Foundation, On pile
11932 |  | - | 115 kV Take-off structure foundation | 4 | Set | 10000 | 40000 | 4 | 40000 | 0
11933 |  | - | 115 kV Disconnecting Switch foundation | 6 | Set | 10000 | 60000 | 3 | 30000 | 0 | 0
11934 |  | - | 108 kV 10kA Lightning arrester foundation | 9 | Set | 5000 | 45000 | 9 | 45000 | 0
11935 |  | - | 115 kV Bus support foundation | 9 | Set | 5000 | 45000 | 9 | 45000 | 0
11936 |  | - | 115 kV Current transformer foundation | 9 | Set | 5000 | 45000 | 9 | 45000 | 0
11937 |  | - | 115 kV Voltage transformer foundation | 12 | Set | 5000 | 60000 | 12 | 60000 | 0
11938 |  | - | 115 kV Circuit-breaker foundation | 3 | Set | 10000 | 30000 | 3 | 30000 | 0
11939 | 6 | Retening wall 3.00 m depth |  | 30 | m | 5000 | 150000 | 0 |  | 0 | 0
11940 | 7 | Lamp post foundation., On 4 x Hex x pile dia 0.15 x 6m. |  | 8 | Set | 5000 | 40000 | 0 |  | 0 | 0
11941 | 8 | Cable trench with steel cover, size 0.80 m and 1.20 m |  | 1 | Lot | 100000 | 100000 | 0 |  | 1 | 100000
11942 | 9 | HDPE Dia 63 mm. PN8 and accessories (for lamp post circuit) |  | 1 | Lot | 20000 | 20000 | 0 |  | 0 | 0
11943 | 10 | Crushed rock No.2 surfacing, 10 cm. height with concrete curb |  | 1 | Lot | 80000 | 80000 | 0 |  | 0 | 0
11944 | 11 | RC Trench with RC cover or PVC pipe in substation (for rain drainge system) |  | 1 | Lot | 50000 | 50000 | 0 |  | 0 | 0
11945 | 12 | RC pipe or PVC. pipe and RC manhole (for control building) |  | 1 | Lot | 50000 | 50000 | 0 |  | 0 | 0
11946 | 13 | Wire mesh fence |  | 1 | Lot | 70000 | 70000 | 0 |  | 0 | 0
11947 | 14 | Mesh gate (rolling door) 6 m width |  | 1 | Lot | 10000 | 10000 | 0 |  | 0 | 0
11948 | 15 | Concrete road 6 m width connect between existing road to substation |  | 1 | Lot | 60000 | 60000 | 0 |  | 0 | 0
11949 | 16 | Civil Engineering design and Permissive Fee (Architecture ,civil) |  | 1 | Lot |  |  | 0 |  | 0 | -
11950 | 17 | Temporary fence and toilet |  | 1 | Lot | 30000 | 30000 | 0 |  | 0 | 0
11951 | 18 | Toilet with sanitary ware |  | 1 | Lot | 30000 | 30000 | 0 |  | 0 | 0
11952 | 19 | งานคืนสภาพพื้นที่ก่อสร้าง |  | 1 | Lot | 50000 | 50000 | 0 |  | 0 | 0
11953 |  | รายละเอียดค่าใช้จ่าย (PART C) อุปกรณ์สำนักงานสำหรับใช้หน้างาน
11954 | 1 | อุปกรณ์ประกอบการใช้งานสนาม
11955 |  | - | เช่าตู้ Mobile Office และโต๊ะ เก้าอี้ทำงาน | 1 | Lot | 5000 | 5000 | 1 | 5000 | 0
11956 |  | - | เช่ารถยนต์ส่วนบุคคล (รถเก๋ง) เกียร์ออโต้ 4 ประตู 4 ที่นั่ง 1,600 ซีซี (อายุไม่เกิน 3 ปี) | 1 | Lot | 0 | 0 | 0 |  | 0 | 0
11957 |  |  | พร้อม พรบ. ประกันชั้น 1 และภาษีประจำปี จำนวน 3 คัน จำนวน 6 เดือน
11958 |  |  | และต้องเป็นรถยนต์จากบริษัทที่ดำเนินธุรกิจรถยนต์เช่า